## Burndown Chart Template
SWE 443 - TEAM BLUE
SPRINT BURNDOWN CHART
| Backlog Item ID | User Stories / Bugs |  | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31
|  |  | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Result
| 1 | Example Product Backlog Item (PBI) Estimated During Sprint Planning | 5 | 2017-03-21: 4; 2017-03-23: -1 | Incomplete | Legend
| 2 | Example Bug Included at the Beginning of Sprint Planning | 2 | 2017-03-29: 2 | Done
| 3 | Example PBI Entered After Sprint Planning (On Day 3) |  | 2017-03-22: -3; 2017-03-29: 3 | Done |  | Missing at Start
| 4 | Example Bug Entered After Sprint Planning (On Day 5) |  | 2017-03-24: -2; 2017-03-28: 2 | Done |  | Added to Sprint
| 5 | Example PBI Entered After Sprint Planning (On Day 6) |  | 2017-03-27: -3; 2017-03-31: 3 | Done
| 6 | Example unstarted task that isn't in current sprint | [11 empty] | -
| 7 | Example unstarted task that isn't in current sprint 2 | [11 empty] | -
| 8 | [12 empty] | -
| 9 | [12 empty] | -
| 10 | [12 empty] | -
| 11 | [12 empty] | -
| 12 | [12 empty] | -
| 13 | [12 empty] | -
| 14 | [12 empty] | -
| 15 | [12 empty] | -
| 16 | [12 empty] | -
| 17 | [12 empty] | -
| 18 | [12 empty] | -
| 19 | [12 empty] | -
| 20 | [12 empty] | -
|  | Remaining Hours | 7 | 7 | 3 | 6 | 7 | 9 | 12 | 10 | 5 | 5 | 2
|  | Ideal Trend | 7 | 6.3 | 5.6 | 4.9 | 4.2 | 3.5 | 2.8 | 2.1 | 1.4 | 0.7 | -1.1102e-15
Note on E5: Note: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on G6: Note: Use a positive number to indicate that the item is complete.
Note on H8: Note: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on S8: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on J9: Note: Use a negative number to indicate that the level of effort just went up during your Sprint.
Note on L9: Note: Use a positive number to indicate that the item is complete.
Note on S9: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on K10: Use a negative number to indicate that your level of effort just went up.
Note on O10: Use this formatting to indicate that you are projecting a number that is not yet final.
Note on P10: Use this formatting to indicate that you are projecting a number that is not yet final.