## Sprint 1
SWE 443 - TEAM BLUE
SPRINT BURNDOWN CHART
|  |  |  | Week 1 |  |  |  |  | Week 2
| Backlog Item ID | User Stories / Bugs |  | 24-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 31-2 | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-06
|  |  | Initial Estimate | Weekend | Mon | Tues | Wed | Thurs | Weekend | Mon | Tues | Wed | Thurs | Result
| 1 | GitHub Set Up | 2 | Week 1 24-26: 2 | Done | Legend
| 2 | Template and Directory Set Up | 1 | [10 empty] | Done | bar: Week 1 24-26
| 3 | User/Account/Bank Stubs | 1.5 | Week 1 24-26: 1.5 | Done |  |  | Missing at Start
| 4 | Create Account | 3 | Week 1 24-26: 1; Week 1 2017-03-27: 0.25; Week 1 2017-03-30: -1; Week 2 31-2: 2.75 | Done |  |  | Added to Sprint
| 5 | Deposit Money | 3 | Week 1 24-26: 2; Week 1 2017-03-27: 0.25; Week 1 2017-03-30: -1; Week 2 31-2: 1.75 | Done
| 6 | Modify Transaction | 3 | Week 1 2017-03-27: 1; Week 2 31-2: -2; Week 2 2017-04-03: 3 | Incomplete
| 7 | Transfer Money | 3 | Week 1 2017-03-29: 0.5; Week 2 2017-04-03: 2.5 | Done
| 8 | Withdraw Money | 3 | Week 1 24-26: 2.5; Week 1 2017-03-30: -1; Week 2 2017-04-03: 1.5 | Done
| 9 | SDMLib Integration (Auto-generate object/class diagrams) |  | Week 1 2017-03-29: -3; Week 1 2017-03-30: 3 | Done | Hours in Sprint
| 10 | Persistence Layer (includes create account, deposit, withdraw, transfer) |  | Week 1 2017-03-29: -8; Week 1 2017-03-30: 2; Week 2 31-2: 5.5; Week 2 2017-04-03: -1.5 | Incomplete |  | Initial Estimate: |  | 45.5
| 11 | Scenario Writing (8) | 5 | Week 1 24-26: 2; Week 1 2017-03-28: 2; Week 2 31-2: 0.25; Week 2 2017-04-03: 0.75 | Done |  | Added Hours: |  | 42.5
| 12 | Welcome Screen | 1 | [10 empty] | Done | Total Hours this Sprint: |  |  | 88 | bar: Week 1 2017-03-27
| 13 | Log In | 3 | Week 1 2017-03-28: 2; Week 2 31-2: 1 | Done |  |  | *not completely accurate
| 14 | Android Research w/ SDMLib (before we start implementing) | 10 | Week 1 24-26: 7; Week 1 2017-03-28: 1; Week 2 31-2: 2 | Done
| 15 | Mockups |  | Week 2 31-2: -6; Week 2 2017-04-04: 2; Week 2 2017-04-05: 2; Week 2 2017-04-06: 2 | Done
| 16 | Class Diagram | [11 empty] | Incomplete | Progress | bar: Week 2 31-2
| 17 | Transaction Log |  | Week 2 31-2: -8; Week 2 2017-04-06: 0.5 | Incomplete |  | Week 1 Progress: |  | 35.5
| 18 | Transaction Fee | [11 empty] | Done |  | Week 2 Progress: |  | 36 | bar: Week 2 2017-04-04 to Week 2 2017-04-05
| 19 | Bugs/Fixes/Optimizations from Week 1 |  | Week 2 31-2: -8; Week 2 2017-04-03: 2; Week 2 2017-04-04: 1; Week 2 2017-04-06: 1 | Incomplete | Total Progress: |  |  | 71.5
| 20 | Burndown Chart Updating/Other Scrum Master Tasks | 7 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | Done |  |  | *not completely accurate
|  | Remaining Hours | 45.5 | 25 | 22 | 16.5 | 26.5 | 24 | 35.25 | 26.5 | 24 | 20.5 | 16.5
|  | Ideal Trend | 45.5 | 40.95 | 36.4 | 31.85 | 27.3 | 22.75 | 18.2 | 13.65 | 9.1 | 4.55 | 0
Note on E5: Note: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on S8: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on S9: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E14: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on I14: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E15: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on I15: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E20: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on K20: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E21: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on K21: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E22: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on K22: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E23: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on M23: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.
Note on E24: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on K24: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.

## Sprint 1.5
SWE 443 - TEAM BLUE
SPRINT BURNDOWN CHART
|  |  |  | Week 1 |  |  |  |  | Week 2
| Backlog Item ID | User Stories / Bugs |  | 2017-04-05 | 2017-04-06 | 7-9 Apr | 2017-04-10 | 2017-04-11 | 2017-04-12 | 2017-04-13 | 14-16 Apr | 2017-04-17 | 2017-04-18
|  |  | Initial Estimate | Wed | Thurs | Weekend | Mon | Tues | Wed | Thurs | Weekend | Mon | Tues | Result
| 1 | Modify Transaction (Undo) | 1 |  | -3 | 3 |  |  |  | 1 |  |  |  | Done | Legend
| 2 | Persistence Layer (includes create account, deposit, withdraw, transfer) | 2 | [5 empty] | 2 |  |  |  |  | Done
| 3 | Class Diagram | 2 |  |  |  |  | 2 | [5 empty] | Done |  |  | Missing at Start
| 4 | Transaction Log + Transaction Class | 8 |  |  |  |  | -1 | 1 |  |  | 7 | 1 | Done |  |  | Added to Sprint
| 5 | Transaction Fee | 1 |  |  | 1 | [7 empty] | Done
| 6 | Transaction Sequence Diagram | 3 | [5 empty] | 2 |  |  |  | 1 | Done
| 7 | Android Integration + Start Android GUI | 16 |  |  |  |  | 0.75 |  | 2.25 | 8 | 2 | 3 | Done
| 8 | Research Networking/Concurrency | [11 empty] | To Do
| 9 | Sales Pitch/Presentation Planning and Completion | 4 | [9 empty] | 4 | Done | Hours in Sprint
| 10 | General Refactoring (Classes, Tests) | 1 | [5 empty] | 1 |  |  |  |  | Done |  | Initial Estimate: |  | 48
| 11 | Class Diagram | 2 |  |  |  |  | 2 | [5 empty] | Done |  | Added Hours: |  | 4
| 12 | Scenario Writing (Transaction Log) | 1 |  |  |  | 1 | [6 empty] | Done | Total Hours this Sprint: |  |  | 52
| 13 | [12 empty] | - |  |  | *not completely accurate
| 14 | [12 empty] | -
| 15 | [12 empty] | -
| 16 | [12 empty] | - | Progress
| 17 | [12 empty] | - |  | Week 1 Progress: |  | 13.25
| 18 | [12 empty] | - |  | Week 2 Progress: |  | 38.75
| 19 | [12 empty] | - | Total Progress: |  |  | 52
| 20 | Burndown Chart Updating/Other Scrum Master Tasks | 7 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | Done |  |  | *not completely accurate
|  | Remaining Hours | 48 | 47.5 | 50 | 44.5 | 43 | 38.75 | 32.25 | 28.5 | 19 | 9.5 | 0
|  | Ideal Trend | 48 | 43.2 | 38.4 | 33.6 | 28.8 | 24 | 19.2 | 14.4 | 9.6 | 4.8 | 0
Note on E5: Note: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on S8: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on S9: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.

## Sprint 2
SWE 443 - TEAM BLUE
SPRINT BURNDOWN CHART
|  |  |  | Week 1 |  |  |  |  | Week 2
| Backlog Item ID | User Stories / Bugs |  | 2017-04-19 | 2017-04-20 | 21-23 Apr | 2017-04-24 | 2017-04-25 | 2017-04-26 | 2017-04-27 | 28-30 Apr | 2017-05-01 | 2017-05-02
|  |  | Initial Estimate | Wed | Thurs | Weekend | Mon | Tues | Wed | Thurs | Weekend | Mon | Tues | Result
| 1 | Finalizing Presentation Plans (Scripts/Scenarios/Bug Fixing) | 3 | 3 | [9 empty] | Done | Legend
| 2 | Last minute adjustments to Android app for demo | 12 | 12 | [9 empty] | Done
| 3 | Continue Integrating Completed Code to Android GUI | 2 | [10 empty] | Incomplete |  |  | Missing at Start
| 4 | Spend time configuring git with our Android project | [11 empty] | To Do |  |  | Added to Sprint
| 5 | Networking (still needs estimate) | [11 empty] | To Do
| 6 | Concurrency (still needs estimate) | [11 empty] | To Do
| 7 | Security (still needs estimate) | [11 empty] | To Do
| 8 | [12 empty] | -
| 9 | [12 empty] | - | Hours in Sprint
| 10 | [12 empty] | - |  | Initial Estimate: |  | 24
| 11 | [12 empty] | - |  | Added Hours: |  | 0
| 12 | [12 empty] | - | Total Hours this Sprint: |  |  | 24
| 13 | [12 empty] | - |  |  | *not completely accurate
| 14 | [12 empty] | -
| 15 | [12 empty] | -
| 16 | [12 empty] | - | Progress
| 17 | [12 empty] | - |  | Week 1 Progress: |  | 15.5
| 18 | [12 empty] | - |  | Week 2 Progress: |  | 0
| 19 | [12 empty] | - | Total Progress: |  |  | 15.5
| 20 | Burndown Chart Updating/Other Scrum Master Tasks | 7 | 0.5 | [9 empty] | Incomplete |  |  | *not completely accurate
|  | Remaining Hours | 24 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5
|  | Ideal Trend | 24 | 21.6 | 19.2 | 16.8 | 14.4 | 12 | 9.6 | 7.2 | 4.8 | 2.4 | 0
Note on E5: Note: Effort calculated using Story Points assigned at Sprint Planning - Enter as a positive Integer
Note on S8: If something is missing at the start of Sprint Planning, place this color box in column E to indicate it was added after the start of the Sprint.
Note on S9: Format the cell of the day that a missing item was added to the Sprint with this color and add in an estimate of story points for the item.